## Gantt Chart
Task Name	Assigned Member	Start Date	End Date	duration(days)	Status
Design Module	krupal	11/1/2025	12/10/2025	40	In Progress
Develop Prototype	kush	11/3/2025	12/7/2025	35	Not Started
Testing & Report	divy	11/11/2025	12/1/2025	21	Not Started